|  |
| --- |
| **TENDER SCHEDULE** |
| **IMPLEMENTING PATRNER:** AGA KHAN RURAL SUPPORT PROGRAMME **PROJECT NAME:** IMPROVED GOVERNANCE OF THE NATIONAL PARKS ACROSS THE WAKHAN CORRIDOR BROGHIL VALLEY UPPER CHITRAL KPK   **PROJECT CODE:**  PAK-AKDN-CHI-003 | DATE: 26/8/2024 |
| **PROCUREMENT PLAN REFERENCE** | **GOODS**[ ]  | **SERVICES**[x]  |
| 1. | Procurement Plan Item No. | 14 |
| 2. | Description of Item | Rehabilitation/improvement of Civil Work (Ghoru MHP 250 kW) |

|  |  |
| --- | --- |
| **EVENT** | **DATE** |
| 1 | Tender notice advertisement | August 27, 2024 |
| 2 | Pre-bid meeting | September 02, 2024, |
| 3 | Deadline for receiving clarifications | September 10, 2024 |
| 4 | Tender closing | September 17, 2024 |
| 5 | Technical bid opening | September 18, 2024 |
| 6 | Technical evaluation | September 18, 2024 |
| 7 | Submission of technical evaluation report to PATRIP Foundation  | September 23, 2024 |
| 8 | Financial bid opening and evaluation | September 30, 2024 |
| 9 | Final evaluation | September 30, 2024 |
| 10 | Submission of final evaluation report to PATRIP Foundation | October 04, 2024 |
| 11 | Submission of draft negotiated contract to PATRIP Foundation | October 14, 2024 |
| 12 | Award communication to bidder/ contract signing | October 24, 2024 |
| 13 | Pre-mobilization meeting with the contractor | October 28, 2024 |
|  |