|  |
| --- |
| **TENDER SCHEDULE** |
| **IMPLEMENTING PATRNER:** AGA KHAN RURAL SUPPORT PROGRAMME **PROJECT NAME:** IMPROVED ROAD INFRASTRUCTURE AND MARKET ACCESS IN IMMIT VALLEY YARKHUN UNION COUNCIL, UPPER CHITRAL KHYBER PAKHTUNKHWA (KPK)**PROJECT CODE:**  PAK-AKDN-GBT-002 | DATE: 10/7/2024 |
| **PROCUREMENT PLAN REFERENCE** | **GOODS**[ ]  | **SERVICES**[x]  |
| 1. | Procurement Plan Item No. | 09 |
| 2. | Description of Item | Rehabilitation & Improvement of Existing Valley Road from Darband to Kishmanja & Rebuilding Bridges (Kankhoon) |

|  |  |
| --- | --- |
| **EVENT** | **DATE** |
| 1 | Tender notice advertisement | July 24, 2024 |
| 2 | Pre-bid meeting | August 05, 2024,  |
| 3 | Deadline for receiving clarifications | August 09, 2024 |
| 4 | Tender closing | August 15, 2024 |
| 5 | Technical bid opening | August 16, 2024 |
| 6 | Technical evaluation | August 16, 2024 |
| 7 | Submission of technical evaluation report to PATRIP Foundation  | August 19, 2024 |
| 8 | Financial bid opening and evaluation | August 29, 2024 |
| 9 | Final evaluation | August 29, 2024 |
| 10 | Submission of final evaluation report to PATRIP Foundation | August 30, 2024 |
| 11 | Submission of draft negotiated contract to PATRIP Foundation | September 10, 2024 |
| 12 | Award communication to bidder/ contract signing | September 20, 2024 |
| 13 | Pre-mobilization meeting with the contractor | September 30, 2024 |
|  |