|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TENDER SCHEDULE** | | | | |
| **IMPLEMENTING PATRNER:** AGA KHAN RURAL SUPPORT PROGRAMME  **PROJECT NAME:** IMPROVED GOVERNANCE OF THE NATIONAL PARKS ACROSS THE WAKHAN CORRIDOR BROGHIL VALLEY UPPER CHITRAL KPK      **PROJECT CODE:**  PAK-AKDN-CHI-003 | | | DATE: 11/03/2025 | |
| **PROCUREMENT PLAN REFERENCE** | | **GOODS** | | **SERVICES** |
| 1. | Procurement Plan Item No. | 20 | | |
| 2. | Description of Item | Supply, Transportation, Installation, testing, and Commissioning of Electromechanical and Transmission & Distribution (T&D) Equipment of Zondrangram and Miragram #01 MHPs | | |

|  |  |  |
| --- | --- | --- |
| **EVENT** | | **DATE** |
| 1 | Tender notice advertisement | March 20, 2025 |
| 2 | Pre-bid meeting | March 28, 2025, |
| 3 | Deadline for receiving clarifications | April 07, 2025 |
| 4 | Tender closing | April 17, 2025 |
| 5 | Technical bid opening | April 18, 2025 |
| 6 | Technical evaluation | April 21, 2025 |
| 7 | Submission of technical evaluation report to PATRIP Foundation | April 24, 2025 |
| 8 | Financial bid opening and evaluation | May 02, 2025 |
| 9 | Final evaluation | May 08, 2025 |
| 10 | Submission of final evaluation report to PATRIP Foundation | May 08, 2025 |
| 11 | Submission of draft negotiated contract to PATRIP Foundation | May 16, 2025 |
| 12 | Award communication to bidder/ contract signing | May 27, 2025 |
| 13 | Pre-mobilization meeting with the contractor | June 10 , 2025 |
|  | | |