AGA KHAN RURAL SUPPORT PROGRAMME

REQUEST FOR PROPOSAL

Annual Outcome study 2025 under

Broadening Economic and Social Transformation for Women’s Economic Empowerment and Recovery (BEST4WEER) project

Submitted by

Monitoring and Evaluation Section

AKRSP, Core Office

Gilgit

Contents

1.	Background	3

2.	The Survey	3

2.1 Objectives of the Survey	3

2.2 Key Indicators of the study	4

2.3 Scope of the study	4

3.	Methodology	4

4.	Activity description for the study	4

5.	Consultant’s ToRs	5

6.	Key Deliverables	5

7.	Data analysis	5

8.	Qualification and Experience of individual/firm	5

9.	Confidentiality and Ownership of the Data, Documents, and Equipment	6

10.	Study Execution Plan	6

10.1	Timelines	6

11.	Hiring Process	6

12.	Application package	6

13.	Evaluation Criteria	6

14.	Ethical/Safeguarding Considerations	7

Annex-1 Outcome Evaluation of Best4weer	8

# Background

The Aga Khan Rural Support Programme (AKRSP) is a programme of the Aga Khan Foundation, Pakistan (AKF, P) which further is an agency of the Aga Khan Development Network (AKDN). The AKDN is a group of private not-for profit, non-denominational international development agencies, institutions and programmes that work primarily in the poorest parts of Africa and Asia to improve the quality of life of communities in remote and resource poor areas. The AKRSP carries out rural development programmes of AKF-AKDN in Gilgit-Baltistan and Chitral (GBC) regions of Pakistan. It works with partners to improve the quality of life by promoting and developing innovative solutions to challenges of development in GBC.

The Broadening Economic and Social Transformation for Women’s Economic Empowerment and Recovery (BEST4WEER) project is a five-year (2021 to 2026), $20.16 million (GAC: $17.41 million; AKFC: $2.75 million) project funded by Global Affairs Canada (GAC). The project is executed by the Aga Khan Foundation Canada (AKFC) and implemented by Aga Khan Foundation Pakistan (AKFP) in partnership with Aga Khan Rural Support Programme (AKRSP) and Accelerate Prosperity (AP). The goal of this community-driven project is to improve women’s social and economic empowerment during the process of COVID-19 recovery and rebuilding in Gilgit-Baltistan province and Chitral district (Khyber Pakhtunkhwa Province), Pakistan. The project has two project components: Economic Inclusion (EI), and Civil Society (CS). Through these interrelated components, BEST4WEER aims to: (1) reduce the social, cultural, institutional, and economic barriers for women’s engagement in economic and social spheres while (2) enhancing the social and economic agency of women. BEST4WEER is coded GE-3, a gender-equality-specific initiative and has been designed specifically to address gender inequalities.

# The Survey

During the last three years, AKRSP has engaged no of young men and women in internship, enterprise development trainings, capacity building of Government officials, voice and leadership and other civil society engagement activities.  As part of the M&E Plan and Results indicators reporting requirements, AKRSP plans to conduct in house outcome study to evaluate the success/learnings of the  above-mentioned support provided to the project beneficiaries. For this purpose, AKRSP is seeking services of a local M&E consultant, for conducting outcome assessment for Best4weer on Year 3 Annual Outcome indicators.

## 2.1 Objectives of the Survey

This outcome study will be carried out to achieve the following main objectives.

- Determine the immediate outcomes of Best4weer for Year 5

- Assess the effectiveness of project activities on project beneficiaries including START training, internship placements.

- Assess the traditional, religious, and CSO leaders with adequate understanding of key gender equality concepts and their ability to promote women’s empowerment

- Assess the Organizational Performance Index of LSO’s and other CSO’s for Best4weer programme area.

- Assess the Knowledge, Attitude and Practice for government officials participating in project capacity building activities in their ability to support women’s social and economic empowerment

- Assess the tracer of participants of Women's voice & leadership trainees through phone tracer survey

- Study PMF and Global indicators and compare trends of employment across implementation levels, and employment sectors

- Assess mandatory global indicators of AKRSP

- Assess the effects of capacity building support provided to beneficiaries through project support activities.

- To identify potential gaps, generate learnings and recommendations to improve future interventions

## 2.2 Key Indicators of the study

The study will cover seven research instruments focussing on separate set of beneficiaries with tools as described in Annex-1.

## 2.3 Scope of the study

The study is mandatory for AKRSP as a reporting requirement of GAC to produce annual results report to assess the immediate outcomes of the project primarily focusing on target beneficiaries benefited from the programme at least three months before the initiation of the study. The list of beneficiaries will be provided by the project team.

# Methodology

The survey method will consist of quantitative tools with structured questions in an interview format. The study tools will be drafted by the core M&E team and refined by the consultant. The participants of the study are beneficiaries from various support activities enterprise development trainings, internship programs and other civil society engagement interventions carried out under Best4weer.

# Activity description for the study

The study frame for the study includes all the beneficiaries of support provided under the project. The beneficiaries come from the target project area of Gilgit, Diamer, Baltistan and Chitral. The consultant will be responsible to refine the sample from the below table. The sample should be drawn keeping in view that representation of implementation level as well as type of support along with gender balance in target group for sampling. The below table reflects the proposed sample frame of the study which will be reviewed and refined in the inception report by the consultant with close coordination with the project team.

| Components | Female | Male | Total |
| --- | --- | --- | --- |
| W&E Component |  |  |  |
| COE tracer survey tool | 10 | 50 | 60 |
| W&E tracer survey tool | 140 | 150 | 290 |
| Total W&E | 150 | 200 | 350 |
| CS Component |  |  |  |
| Voice and leadership trainees tracer tool | 300 | 0 | 300 |
| OPI tool CSOs/LSOs/WOs (14 LSOs, 36 WOs ) | 36 | 14 | 50 |
| Government Officials KAP tool | 20 | 30 | 50 |
| Traditional, Religious and CSO leader Tracer survey | 40 | 40 | 80 |
| Total CS | 396 | 84 | 400 |
| Grand Total | 546 | 284 | 750 |

This is tentative, actual to be updated with MERL team AKRSP

# Consultant’s ToRs

The consultant will be responsible for following task.

- Draft an inception report, receive feedback from AKRSP and incorporate feedback. The inception report should discuss in detail the study plan, methodology, sampling scheme, survey tool and survey protocols,

- The consultant will work MERL team AKRSP in cleaning and aligning the data for sample finalization.

- Hire and train the local experienced data collection team for the survey with consultation with MERL team.

- Conduct pilot testing and refine the tools (if it is required) in consultation with AKRSP,

- Develop survey manuals/guidelines and iimplement the full-scaled study,

- Collect data from the field/beneficiaries with the support of AKRSP field teams

- Maintain database in MS Excel and submit the database with analysis to AKRSP at the end of the study,

- Prepare and submit a draft survey completion report to the AKRSP on the agreed template and on agreed deadline,

- Present findings based on the draft report in a workshop and receive feedback,

- Incorporate any feedback provided by AKRSP on the report and the findings to the Annual Results Report.

- Develop the final report Outcome Report and Annual Results Report which includes findings of the assessment and agreed feedback to be submitted within a week after the validation workshop

# Key Deliverables

The consultant will submit the work in the form of a final report on  an agreed template of AKRSP. Overall, the report should cover the overall objectives/purpose and scope of the work. Specifically, the report should discuss in detail:

- Inception Report including refining methodology, training enumerators, workplan with final tools and data collection plan-15 days

- Draft report with initial tables/ findings on indicators for outcome study-25 days(Annex 1)

- Final Report(Outcome study/Annual results Report) with incorporation of feedback-20 days

# Data analysis

The consultant will analyze data through descriptive analysis to assess the outcome indicators and infographics to highlight key findings. The findings will further elaborate the existing gaps and will be helpful in developing recommendations for the project.

# Qualification and Experience of individual/firm

The consultant/firm should include the technical expertise and practical experience required to deliver the scope of work and evaluation outputs, in particular, with regards to:

- Consultant or team of consultant should have a master’s degree in statistics, economics, social sciences, or other development studies

- Demonstrated experience in conducing similar studies(outcome studies/impact assessments and evaluations)

- Knowledge and experience in conducting research and evaluation studies in Gilgit-BBaltistan and Chitral.

- Demonstrated experience in safeguarding and respecting vulnerable populations,

- Fluency in English and Urdu is mandatory. Additional relevant languages (e.g., Khowar, Shina, and Wakhi etc), an asset.

# Confidentiality and Ownership of the Data, Documents, and Equipment

- AKRSP shall be the owner of all the data collected, data sets, reports, documents, etc. prepared by the consultant,

- All the data collected must be handed over to AKRSP before final payment,

- All documents, reports and information from this assignment will be regarded as AKRSP's intellectual property, so the mentioned outputs or part of it cannot be sold or used in any case without the prior permission of AKRSP.

# Study Execution Plan

# Timelines

The core M&E team will be responsible for the conceptual design and contract out outcome study. As per ToRs, the consultant will be responsible for collecting data and produce a consolidated draft narrative report incorporating analysis of findings against each indicator by Dec 31, 2025.

# Hiring Process

AKRSP will hires services of consultant through competitive process, inviting bids and evaluating bids.

# Application package

Applicants are required to submit following as part of the application package.

1. Profile consist of following details.

- Willingness to work under strict timelines,

- Relevance of the candidate with the scope of work,

- Ability of the candidate to deliver the deliverables,

- Local Team members(If any) and dedication for executing the task

- Budget/renumeration expectations.

2. Technical proposal with detailed methodology and study execution plan and annex sample of work (two relevant studies)

3. Financial proposal with details of cost elements

# Evaluation Criteria

Proposals will be evaluated based on the following set of criteria:

| CRITERIA | MAXIMUM SCORE |
| --- | --- |
| Technical Component |  |
| Demonstrated experience in conducting and coordinating similar studies | 25 |
| Education and Technical Experience of Team | 15 |
| Proposed Methodology, Workplan and Approach(Gender lense and technical) | 30 |
| Relevance of Sample work to study | 10 |
| Total Technical Component | 80 |
| Financial Component |  |
| Realistic and appropriate costs for proposed work | 10 |
| All relevant costs included to carry out proposed work | 10 |
| Total Financial Component | 20 |
|  | 100 |

# Ethical/Safeguarding Considerations

The responses will be taken after the consent of the respondents. The consent question will be added in the beginning of the questionnaire/tool. The consent will be taken after informing objectives and purpose of the survey and abiding by the AKRSP’s safeguarding policy.

AKRSP-AKF is an Equal Opportunity Employer and is Committed to Safeguarding and Promoting the Welfare of Children and Vulnerable Adults and Expects all Staff and Partners to Share this Commitment.

# Annex-1 Outcome Evaluation of Best4weer

Consultant will update below indicators with MERL team, the team leads may include more indicators depending on the needs of the project and upcoming POC meeting in December 2025.

| Tool | Sampling Unit | Indicators to capture |
| --- | --- | --- |
| Women's Empowerment Principles Gap Analysis Tool (WEPs 001) | CoE members (3) | 1100.2. % of Coalition of Employers members who have adopted gender responsive policies and practices (by sector) |
| Organizational Performance Index Tool (OPI 001) | LSOs/CSOs | % of CSOs with improved performance (by CSO type, implementation level) |
| Traditional & CSO leaders phone tracer survey (Tracer 001) | Traditional, religious & CSO members | 1110.1 % of traditional, religious and CSO leaders with adequate understanding of key gender equality concepts (by gender, implementation Level, type of entity) 1110.2 Degree of confidence of traditional, religious and CSO leaders in their ability to promote women’s empowerment (by gender, implementation level, type of entity) |
| Work & enterprise graduates phone tracer survey (Tracer 002) | AP incubation & acceleration graduates | 1120.1 % of self-employed female direct beneficiaries who have accessed market services supported* by BEST4WEER (by age group, type of service, implementation Level) *financially or technically supported 1120.2 % of male graduates from the entrepreneurship and the employable skills program who are supportive of women working in equal positions at equal pay in their sector (by age group, sector, Implementation level) 1210.1 % of graduates who attained improved employment status 12 months after completion of a project-supported training program (by gender, sector, age group, Implementation level) 1210.3 % of graduates working in climate-related sectors or businesses (by gender, age group, implementation level) 1220.1 # of full-time job equivalents created and sustained* in project-supported enterprises (by gender, age group, new jobs vs. sustained jobs, implementation level) *Sustained = jobs that have been retained after 1 year by businesses supported under project entrepreneurship activities 1220.2 % of supported Small and Growing Businesses (SGBs) with increased revenue following project support (by gender of entrepreneur, age group of entrepreneurs, implementation level) 1220.3 Value (PKR) of private sector investment leveraged by enterprises supported by the project (by entrepreneur gender, age group of entrepreneur, implementation level) |
|  | AKRSP START graduates |  |
|  | Internship graduates |  |
|  | Employable skills/future of work graduates |  |
| Coalition of Employers phone tracer survey (Tracer 003) | CoE members hosting employer-level training programs | 1120.3 F/M ratio of workforce (new recruits only) of Coalition of Employers members (by job level (seniority), sector) 1210.2 % of Coalition of Employers members hosting employer-led training programs satisfied with the skills of trainees (by gender, sector) |
| Women's voice & leadership trainee phone tracer survey (Tracer 004) | Women trainees from the following programs: life skills, influencers, sports and creative arts, VERTs, CBSGs, women councillors holding elected office | % of women participating in project-supported voice and representation initiatives who feel their opinion has been heard in household and community decision making processes (by age group, implementation Level) % of women participating in project-supported voice and representation initiatives who have set individual goals and believe they can achieve them in the next 12 months (by age group, implementation Level) |
| Knowledge, attitude and practice government phone survey (KAP 001) | Government officials participating in project capacity-building activities | 1130.2 Degree of confidence of government officials participating in project capacity building activities in their ability to support women’s social and economic empowerment (by gender, implementation level, department) |
| Mandatory Global Indicators CS |  |  |
| CS Global Outcome tool | LSOs/CSOs | CS10.0 % of issues articulated by civil society that are acted upon by decision makers |
| CS Global Outcome tool | LSOs/CSOs | CS11.0: Monetary value (USD) of support raised from local donors by CSOs |
| CS Global Outcome tool | LSOs/CSOs | CS8.0: % of CSOs and sub-national government agencies with improved performance |
| CS Global Outcome tool | LSOs/CSOs | CS10.0 % of issues articulated by civil society that are acted upon by decision makers |
| CS Global Outcome tool | LSOs/CSOs | CS11.0: Monetary value (USD) of support raised from local donors by CSOs |
| CS Global Outcome tool | LSOs/CSOs | CS9.0: Extent to which members of the target population value the work of CSOs or sub-national government agencies (Net Promoter Score) |
| CS Global Outcome tool | LSOs/CSOs | CS12.0: # of people directly reached by civil society interventions |