Terms of Reference (TOR)

For

Production of Documentary and Audiovisual Products

for the BEST4WEER Project

Project Locations: Gilgit-Baltistan and Chitral

Project: Broadening Economic and Social Transformation for Women's Economic Empowerment and Recovery (BEST4WEER)

Aga Khan Rural Support Programme (AKRSP)

- About AKRSP: The Aga Khan Rural Support Programme (AKRSP) is a pioneering rural development non-profit organisation, established in 1982 to help improve the quality of life of the local communities in Gilgit-Baltistan and Chitral. Registered under the Companies Act, 2017 with the Securities and Exchange Commission of Pakistan (SECP), AKRSP approach is community-led and encourages equitable social and economic development in the region.

AKRSP has been working across all 10 districts of Gilgit-Baltistan and two districts of Chitral in Khyber Pakhtunkhwa (KPK). In 2024, AKRSP expanded its programme to two districts of Sindh-Thatta & Sujawal, further extending its impact and continuing its mission of improving the quality of life for rural communities across Pakistan.

AKRSP works across several key thematic areas to foster sustainable development and build resilience in the communities it serves. These thematic areas include agriculture and food security, climate resilience, health and nutrition, education, early childhood development, civil society, and work and enterprise. By integrating these focus areas into its development interventions, AKRSP aims to create holistic, community-driven solutions that address the multifaceted needs of the local communities

- Introduction to the Project: The Broadening Economic and Social Transformation for Women's Economic Empowerment and Recovery (BEST4WEER) Project is being implemented by the Aga Khan Rural Support Programme (AKRSP) in partnership with the Aga Khan Foundation (AKF), with financial support from Global Affairs Canada (GAC). Over the past five years, the project has contributed to advancing women's economic empowerment and gender equality across GBC through interventions focused on livelihoods, entrepreneurship, leadership, financial inclusion, social norm change, and community engagement.

As the project concludes, a comprehensive documentary and associated audio-visual products will be developed to document its legacy, celebrate achievements, and capture the stories, experiences, and transformations of women, families, and communities.

AKRSP therefore intends to engage a Service Provider to produce a flagship end-of-project documentary, supported by digital reels and a professional photography archive. Together, these products will document the implementation journey, achievements, lessons learned and lasting impact of the BEST4WEER Project while strengthening donor visibility, institutional knowledge management, stakeholder engagement and public awareness.

- Objective of the Assignment: The overall objective of this assignment is to produce a flagship end-of-project documentary, supported by digital reels and professional photography, that combines compelling storytelling, authentic human experiences and high production values to document the BEST4WEER Project and serve as a lasting institutional knowledge and communication resource. Specifically, the assignment seeks to:

- Produce a professionally crafted end-of-project documentary, thematic digital reels and high-quality photography for communication, visibility, advocacy, knowledge management and donor reporting.

- Document the implementation journey, key interventions, achievements, innovations, lessons learned and long-term impact of the BEST4WEER Project.

- Showcase the transformative impact of the project's interventions on women empowerment, enterprise development, civil society strengthening, gender equality and inclusive development.

- Capture stories, perspectives and experiences of beneficiaries, communities, institutions and other stakeholders through compelling visual storytelling.

- Strengthen donor visibility, stakeholder engagement and public awareness through engaging audiovisual communication products.

- Create a lasting repository of high-quality audiovisual assets to support organisational learning, future communications and institutional knowledge management.

- Target Audience:

The documentary and associated audiovisual products are intended for:

- Development partners and donor agencies;

- Government institutions and policymakers;

- Civil society organisations and community institutions;

- Women's organisations, enterprise support institutions and private sector partners;

- National and international development practitioners;

- Academic and research institutions;

- Media organisations and digital media platforms;

- Project beneficiaries and local communities;

- Participants of project close-out, dissemination and knowledge-sharing events; and

- Other stakeholders interested in women's economic empowerment, gender equality and inclusive development.

- Scope of Work

The selected Service Provider shall be responsible for the planning, production and post-production of a flagship end-of-project documentary, thematic digital reels and a professional photography archive documenting the implementation journey, achievements, lessons learned and long-term impact of the BEST4WEER Project.

The Service Provider shall exercise sound creative and editorial judgement throughout the assignment to produce a compelling documentary that balances factual accuracy with authentic human stories and visual storytelling, ensuring that the final production reflects both the technical achievements and the transformative impact of the BEST4WEER Project.

The assignment shall include, but not be limited to, the following tasks:

Inception and Production Planning

- Hold inception meetings with the AKRSP Communications Section and BEST4WEER Project Team to obtain a comprehensive understanding of the project, communication objectives, target audiences and expected outputs.

- Review available project documentation, reports, publications, and other communication materials.

- Develop the documentary concept, storyline, narrative structure, script outline, production schedule, filming plan and post-production workflow for approval prior to field production.

- Prepare an Inception Report detailing the proposed methodology, work plan, production schedule, quality assurance process and risk mitigation measures.

Research and Content Development

- Conduct consultations and interviews with relevant project staff and stakeholders to strengthen the documentary narrative and ensure technical accuracy.

- Review and synthesise project documentation to identify key achievements, lessons learned, innovations and evidence of impact.

- Develop documentary scripts, interview guides, narration and storyboards for approval by AKRSP.

- Ensure the documentary reflects authentic, balanced and evidence-based stories highlighting women's economic empowerment, enterprise development, civil society strengthening, gender equality and inclusive development.

Field Production

- Undertake field production across selected BEST4WEER intervention areas in Gilgit-Baltistan and Chitral.

- Capture high-quality video footage, professional photography and interviews covering project interventions, beneficiary experiences, community institutions, enterprise development, stakeholder perspectives and evidence of change.

- Capture supporting footage, including landscapes, community life, project activities and aerial footage (where appropriate and legally permissible), to strengthen the documentary narrative.

- Generate sufficient visual content to support the documentary, digital reels and institutional photography archive.

- Personal interviews of change with change agents and observational footages that captures daily realities of life for the selected case/or cases in the documentary.

Post-Production

- Produce a professionally crafted end-of-project documentary of approximately 15–20 minutes, integrating interviews, narration, project footage, archival material, graphics and supporting visuals into a compelling and coherent narrative.

- The documentary shall be produced to professional broadcast-quality standards, demonstrating excellence in storytelling, cinematography, editing, sound design, colour grading, motion graphics and overall production value suitable for institutional, national and international audiences.

- Produce thirty (30) professionally edited digital reels of approximately 60–120 seconds each for social media and digital dissemination.

- Post-production editing need to show a clear journey of overcoming systemic barriers, integrating data from project with individual stories of change.

- Undertake editing, motion graphics, animation (where appropriate), colour grading, sound design, audio mixing, subtitling and final mastering to professional broadcast standards.

- Produce a comprehensive library of professionally edited, high-resolution photographs captured during field production.

- Ensure all audiovisual products comply with AKRSP, AKF and Global Affairs Canada branding and visibility requirements.

Review, Revision and Quality Assurance

- Submit the documentary and associate audiovisual products for review and approval before delivery of the final outputs.

- Incorporate comments received from AKRSP, AKF and designated reviewers through the agreed review process.

- Subject all draft and final outputs to comprehensive internal editorial and technical quality assurance prior to submission to AKRSP.

Final Production and Submission

- Deliver all final audiovisual products in formats suitable for broadcast, digital dissemination and institutional archiving.

- Submit organised raw video footage, project files, photographs, interview recordings and other production assets in editable digital format.

- Ensure that all deliverables are original, free from copyright infringement and produced in accordance with internationally accepted audiovisual production standards.

- Deliverables The Service Provider shall deliver the following outputs:

- Inception Report, including the documentary concept, storyline, methodology, work plan, production schedule and filming plan.

- Approved Script and Storyboard for the documentary, together with interview guides and narration script.

- Rough Cut of the Documentary for technical and editorial review.

- Final End-of-Project Documentary (approximately 15–20 minutes) in high-resolution formats suitable for broadcast, digital dissemination and institutional archiving.

- Documentary Trailer (90–120 seconds)

- Thirty (30) Professionally Produced Digital Reels (approximately 45–90 seconds each) optimised for digital and social media platforms.

- Professional Photography Archive, comprising a minimum of 200 edited high-resolution photographs covering project interventions, beneficiaries, events, landscapes and other relevant themes.

- Raw Production Assets, including organised raw video footage, photographs, interview recordings, drone footage (where applicable), project files and associated production assets on a portable external SSD.

- Required Qualification and Experience: The eligible applicants may be service providers with demonstrated experience in documentary production and development communications. Preference will be given to applicants who demonstrate:

- Minimum five (5) years of demonstrated experience in documentary filmmaking, audiovisual production and visual storytelling.

- Demonstrated experience in producing flagship documentaries, institutional films or development communication products for national or international development organisations, UN agencies, bilateral donors, INGOs or government programmes.

- Experience working on development projects focused on women empowerment, gender equality, inclusive development and knowledge management.

- Demonstrated expertise in documentary direction, scriptwriting, cinematography, photography, editing, motion graphics, colour grading, sound design and post-production.

- A portfolio of at least five (5) comparable documentary or institutional film productions completed during the past five years.

- Availability of a qualified multidisciplinary team, including a Creative Director/Documentary Director, Producer, Cinematographer, Photographer, Editor and Motion Graphics Specialist.

- Duration of Assignment: The duration of the assignment shall be forty-five (45) calendar days from the date of signing the contract. The assignment is expected to commence in August 2026 and be completed by mid-September 2026.

- Proposed Payment Schedule

|  | Milestone | Deliverables | Timeline | Payment |
| --- | --- | --- | --- | --- |
| 1 | Inception Phase | Submission and approval of the Inception Report, documentary concept and production plan | Within 7 calendar days of contract signing | 20% |
| 2 | Draft Submission | Submission of the documentary rough cut and sample digital reels for review | Within 30 calendar days of contract signing | 30% |
| 3 | Final Submission | Submission and approval of all final deliverables, including the documentary, digital reels, photography archive and raw production assets | Within 45 calendar days of contract signing | 50% |

J. Application Package: Interested Service Provider(s) shall submit the following:

1. Cover Letter: A signed cover letter expressing interest in the assignment and confirming acceptance of these Terms of Reference and the proposed timeline.

2. Profile: A brief profile of the Service Provider highlighting relevant experience in documentary production, audiovisual storytelling, cinematography, photography and production of communication and knowledge management products.

3. Technical Proposal: The Technical Proposal shall clearly demonstrate the Service Provider's understanding of the assignment, creative vision and technical capability to produce a flagship documentary and associated audiovisual products. At a minimum, it shall include:

- Understanding of the assignment and proposed approach;

- Creative Treatment (2–4 pages) outlining the proposed documentary narrative, visual style, storytelling approach, interview strategy, cinematographic treatment, use of archival material, graphics, music and overall creative direction;

- Proposed production methodology covering research, script development, filming, photography, post-production and quality assurance;

- Work plan and production schedule;

- Team structure, key personnel and their respective roles and responsibilities;

- Proposed production equipment, software and technical resources;

- Quality assurance and review process; and

- Any innovative or value-added approaches that will enhance the quality, impact and visual appeal of the documentary and associated audiovisual products.

4. Curriculum Vitae (CVs)

Updated CVs of the proposed key personnel relevant to the assignment.

5. Relevant Experience and Work Samples

Evidence of at least 3-5 similar documentary or audiovisual assignments completed during the past five years.

6. Financial Proposal

A separate Financial Proposal indicating the total lump-sum cost of the assignment, including a detailed cost breakdown and applicable taxes.

Note: AKRSP reserves the right to seek clarification or additional supporting documentation during the evaluation process. Such clarification shall not permit applicants to materially alter the content or pricing of their proposals after the submission deadline.

- Intellectual Property Rights

All documentary footage, digital reels, photographs, scripts, storyboards, interview recordings, graphics, animations, source files, project files, raw footage and other materials developed under this assignment shall become the sole intellectual property of AKRSP upon full payment of the contract.

The Service Provider shall not reproduce, publish, distribute or use any material produced under this assignment without the prior written approval of AKRSP.

- Confidentiality

The Consultant/Service Provider shall maintain strict confidentiality regarding all project information, documents, photographs, video footage, beneficiary information and other materials accessed during the assignment. Such information shall not be disclosed to any third party without the prior written consent of AKRSP.

The Consultant/Service Provider shall ensure that informed consent is obtained for all newly recorded interviews and identifiable photography or videography, where required, and that all materials are produced in accordance with applicable ethical standards.

- Safeguarding and Informed Consent

- The Service Provider shall comply with AKRSP and AKF safeguarding policies throughout the assignment.

- Informed consent shall be obtained from all individuals who are photographed, filmed or interviewed.

- For minors, adolescent girls, persons with disabilities (PWDs) and other vulnerable groups, prior consent from parents or legal guardians shall be obtained.

- All engagement shall respect dignity, privacy, cultural sensitivities, and the principle of do no harm.

- Submission Guidelines: Interested parties must submit their technical and financial proposals to AKRSP Procurement Section no later than 5:00 PM on 31 July 2026.

The Technical and Financial Proposals must be submitted to the address below in separate sealed envelopes, clearly marked with the name of the proposal and the project title.

Or submit your proposals to the email to procurement_akrsppk@akdn.org; clearly mention the subject with the name of the proposal and the project title

For further inquiries or additional information, please contact the Procurement Manager at the number provided below.

Manager Procurement

Aga Khan Rural Support Programme (AKRSP)

Head Office, Babar Road, Gilgit

Phone: 05811-452480

AKRSP is an equal opportunity organisation. Qualified women, women-led firms, and service providers are encouraged to apply.

Note: AKRSP reserves the right to accept or reject any or all proposals, and to cancel, suspend, or terminate this Request for Proposals (RFP) or the procurement process at any stage without assigning any reason or incurring any liability. AKRSP shall not be obliged to award the assignment. Incomplete or late submissions will not be considered.