AGA KHAN RURAL SUPPORT 
PROGRAMME (AKRSP)

─────────────────────────────────────────────────────────────────────────────────────

STANDARD BIDDING DOCUMENT

CIVIL WORKS OF SONOGHORE PARWAK
500 kW MINI HYDROPOWER PROJECT

PROCUREMENT

Lot 1: Hydropower Channel Portion-1 RD 00 to RD 2100

Single Stage – Two Envelope bidding Procedure

| Item | Information |
| --- | --- |
| Tender Reference | CIVIL WORKS OF SONOGHORE PARWAK 500 kW MINI HYDROPOWER 2026 EU |
| Project Location | Sonoghore Parwak, Upper Chitral, Khyber Pakhtunkhwa |
| Implementing Partner | Aga Khan Rural Support Programme (AKRSP) |
| Bid Currency | PKR |

# DOCUMENT STRUCTURE

PART I – BIDDING PROCEDURES

Section 0 – Invitation to Bid and Project Information

Section 1 – Instructions to Bidders (ITB)

Section 2 – Bid Data Sheet (BDS)

Section 3 – Bidding and Qualification Forms

Section 4 – Bill of Quantities (BoQ)

PART II – IMPLEMENTING PARTNER’S REQUIREMENTS

Section 5 – General Specifications

Section 6 – Particular / Technical Requirements

PART III – CONTRACT FORM AND CONDITIONS

Section 7 – Contract Form

Section 8 – Conditions of Contract

PART IV – SCOPE OF WORKS AND DESIGN INFORMATION

Section 9 – Scope of Works and Drawings / Design Information

Annexes

This document is intended to be read together with the approved drawings, technical specifications, BoQs, addenda and other documents issued as part of the tender.

# PART I – BIDDING PROCEDURES

## SECTION – INVITATION TO BID AND PROJECT INFORMATION

### Invitation to Bid

Aga Khan Rural Support Programme (AKRSP) invites sealed bids from eligible and qualified contractors for the civil works of the Sonoghore Parwak 500 kW Mini Hydropower Project in Upper Chitral, Khyber Pakhtunkhwa, Pakistan, under European Union-supported financing and applicable AKRSP procurement requirements.

### Project Background

The Sonoghore Parwak 500 kW Mini Hydropower Project is a new hydropower development intended to increase renewable energy generation capacity and improve access to reliable and affordable electricity in the target area of Upper Chitral. The civil works under this tender form part of the water conveyance system required for the MHP.

The project forms part of the Energy Plus: Energy for Climate Resilience in Gilgit-Baltistan (GB) and Upper/Lower Chitral districts in Khyber Pakhtunkhwa (KP). The Action is coordinated by Aga Khan Foundation, Portugal, with AKF Pakistan, AKRSP, Accelerate Prosperity (AP) and NPAK Energy Limited (NEL) as partners.

The Energy Plus Action supports renewable energy generation, improved energy access, climate resilience and sustainable socio-economic development, with particular attention to communities having limited or unreliable access to affordable energy.

### Purpose of the Works

Construction of hydropower channel civil works and associated structures for the Sonoghore Parwak 500 kW MHP portion-1

Execution of the Works in accordance with approved drawings, technical specifications and BoQ quantities.

Delivery of durable and properly finished civil works suitable for the intended hydraulic and structural function.

### Important Tender Conditions

Technical/qualification and financial documents shall be submitted in separate envelopes.

No part of the Works may be subcontracted. Ordinary purchase of materials from suppliers is permitted.

AKRSP will depute a Site Engineer to guide and monitor progress and quality.

The Contractor remains fully responsible for workmanship, quality, safety and timely completion.

## SECTION 1 – INSTRUCTIONS TO BIDDERS (ITB)

### Scope of Tender

The Contractor shall execute and complete all Works included in the approved BoQ, drawings and technical specifications. The Contractor shall provide labour, materials, equipment, transport, temporary works, setting out, testing, protection and all other inputs required for complete execution.

### Lot-wise Bidding and Award

Bidders may submit bids for Lot 1, Lot 2, or both Lots. Lot 1 shall be opened and evaluated first and shall be considered for award before Lot 2. A bidder awarded Lot 1 shall not be considered for award of Lot 2. If a bidder submits bids for both Lots but is not awarded Lot 1, its bid for Lot 2 may be evaluated and considered for award in accordance with the requirements of the Bidding Documents.

A bidder shall not submit bids for different Lots under different company names, legal entities, trade names, or other identities in order to avoid or bypass this requirement. Any material misrepresentation or attempt to bypass the Lot-wise bidding and award requirements may result in rejection of the affected bid(s) as non-responsive and/or disqualification from the procurement process.

### No Right to Other Works

Award of one Lot shall not create any right, preference or expectation of award of the other Lot or any other works of the MHP.

### Eligible Bidders

The bidder shall be legally eligible to undertake the Works in Pakistan, possess the required PEC registration, satisfy the qualification requirements and not be subject to applicable debarment, exclusion or legal restriction.

### Previous Performance with AKRSP

Bidders who have previously undertaken works or contracts with AKRSP and have unsatisfactory performance may be declared ineligible for this tender. Such cases may include, but are not limited to, litigation, serious or persistent failure to perform contractual obligations, abandonment of works, repeated non-compliance with technical specifications or quality requirements, unjustified delays, failure to rectify notified defects, serious contractual breaches, or termination due to Contractor default.

### Conflict of Interest

Bidders shall disclose any actual or potential conflict of interest. AKRSP may reject a bid where a conflict is material and cannot reasonably be addressed.

### Fairness, Integrity and Prohibited Practices

Bidders shall observe the highest standards of integrity and shall not engage in fraud, corruption, collusion, coercion, obstruction, misrepresentation or other prohibited practices. Such conduct may result in rejection, cancellation of award, termination or other action permitted by law and AKRSP requirements.

### Eligible Materials and Equipment

Materials and equipment shall be new unless otherwise specified and shall comply with the approved drawings, specifications and applicable standards. The Contractor shall provide certificates, test reports and samples where required.

### Pre-tender meeting or site visit

## The bidder is advised to attend any pre-tender meeting personally or Engineer of the firm.

## The bidder is advised to visit and examine the site of works and its surroundings and obtain all site information that may be necessary for preparing the tender and entering into a contract for construction of the works. The cost of visiting the site shall be at the bidder’s expense.

## Bidders must submit any questions in writing, to reach the AKRSP not later than one week before the pre-bid meeting.

## Non-attendance at the pre-bid meeting will be a cause for disqualification of a Bidder.

The Pre bid meeting will be held on    19/ 10 / 2026 at Regional Programme office AKRSP Chitral.

### Clarifications

Requests for clarification shall be submitted in writing within the period stated in the BDS. AKRSP may issue written clarifications or addenda, which shall form part of the tender documents.

### Amendment of Tender Documents

AKRSP may issue addenda before the submission deadline. Bidders shall acknowledge and incorporate all issued addenda in their bids. Where necessary, the deadline may be extended to provide reasonable time for bidders to respond.

### Language of Bid

The qualification document as well as all correspondence and documents relating to the qualification shall be in English language. Supporting documents and printed literature, that are part of the application, may be in another language.

### Documents Comprising the Bid

The bid shall comprise the technical/qualification documents, bid security, financial bid, priced BoQ, signed declarations and other documents specified in the BDS.

### Technical Envelope (inner envelop 1)

The Technical Envelope shall contain all qualification and technical documents. No financial price shall be included in the Technical Envelope.

### Financial Envelope (inner envelope 2)

The Financial Envelope shall contain the signed Letter of Bid, Rate analysis and priced BoQ for the tendered work.

### Tender Prices

Quoted rates shall include all costs required for the complete execution of the Works, including applicable taxes, duties, transportation, testing, temporary works, overheads, supervision, profit, and any potential cost escalation during the entire construction period. The quoted rates shall remain fixed, and no further price escalation or adjustment shall be allowed for the Project.

### Currency

The Bid shall be quoted entirely in Pakistani Rupees (PKR), and all payments under the Contract shall be made in PKR, subject to applicable laws, taxes, and the terms and conditions of the Contract.

### Tender Validity

Bids shall remain valid for the period stated in the BDS. AKRSP may request an extension where permitted, but bidders shall not be required to change their prices as a condition of such extension.

### Bid Security

The bidder must submit Bid Security in the form of a Call Deposit Receipt (CDR) for the fixed amount specified in the Bidding Data Sheet (BDS). The CDR must be valid, properly issued, and submitted with the bid as required. Failure to provide the required and acceptable Bid Security may result in the bid being declared non-responsive and rejected.

### Alternative Bids

Alternative designs or alternative bids are not permitted.

### Taxes and Duties

The bidder/Contractor shall ensure that all applicable taxes, duties, levies, fees, and other government charges payable under the prevailing laws are fully included in the quoted bid prices. No additional payment shall be made by AKRSP for such costs after award of the contract.

Where required by applicable law, AKRSP shall deduct the applicable withholding tax and other statutory deductions from payments due to the Contractor and deposit the deducted amount with the relevant government authority on behalf of the Contractor.

The Contractor shall be solely responsible for fulfilling all applicable tax and statutory requirements, including registration, filing of returns, payment of taxes, and submission of required documents to the relevant government authorities. Any liability arising from non-compliance shall remain the responsibility of the Contractor.

### Bid Submission

Bids shall be prepared and submitted strictly in accordance with the manner, format, place, and deadline specified in the Bidding Data Sheet (BDS). The bidder shall ensure that the complete bid, including all required forms, supporting documents, bid security, and other information specified in the bidding documents, is submitted before the stipulated deadline.

The bid must be delivered to the designated submission address/place and within the date and time specified in the BDS. The bidder shall be solely responsible for ensuring timely delivery and for allowing sufficient time for any transportation, courier, or other delivery arrangements.

Any bid received after the specified submission deadline, regardless of the reason for the delay, shall be considered late and shall not be accepted or considered for evaluation. The Procuring Organization shall not be responsible for delays caused by courier services, postal services, transportation issues, technical problems, force majeure, or any other circumstances beyond its control.

Bidders are therefore advised to submit their bids well before the deadline to avoid any risk of late submission.

### Bid Opening

The Technical Envelopes shall be opened and evaluated in accordance with the procedure specified in the bidding documents. The Financial Envelopes of all bidders shall remain sealed and shall only be opened for those bidders who are found technically qualified and substantially responsive to the requirements of the tender. Financial Envelopes of technically disqualified or non-responsive bidders shall not be opened.

### Examination of Bids

AKRSP shall determine whether each bid is complete and substantially responsive to the tender requirements. Material deviations, reservations or omissions may result in rejection.

### Clarification of Bids

AKRSP may seek clarification from a bidder where permitted. Clarification shall not change the substance or price of the bid, except correction of arithmetic errors where applicable.

### Qualification Evaluation

Qualification shall be evaluated against the minimum requirements in the BDS. AKRSP may verify submitted information with clients, authorities and other relevant sources.

### Financial Evaluation

Only the financial bids of technically qualified and substantially responsive bidders shall be evaluated. Arithmetic errors shall be corrected in accordance with the tender procedure, and the bidder shall be bound by the corrected result where applicable.

### Lowest Responsive Evaluated Bid

Subject to responsiveness, qualification and applicable procurement requirements, award shall normally be made to the bidder with Technically qualified and with the responsive financial bid for the tendered work.

### Unbalanced Bids

Where a bid appears materially unbalanced or front-loaded, AKRSP may seek reasonable clarification or additional security where permitted by the applicable procurement requirements and Contract.

### AKRSP’s Right to Accept or Reject

AKRSP reserves the right to accept or reject any bid, reject all bids, cancel the tender or decline to award the tendered work.

### Notification and Contract Award

The successful bidder shall be notified in writing. The Letter of Acceptance and signed Contract Agreement, together with the required Performance Security, shall establish the contractual obligations in accordance with the tender documents.

### Performance Security

The successful bidder shall furnish the required Performance Security in the amount, form, and within the period specified in the Bidding Data Sheet (BDS) and the tender documents. The Performance Security shall be valid for the period specified in the contract and shall be submitted in an acceptable form issued by a recognized bank or financial institution, as applicable.

Failure of the successful bidder to submit the Performance Security within the stipulated period shall constitute a failure to comply with the conditions of award and may result in cancellation of the award, forfeiture of the Bid Security, where applicable, and/or any other remedies available to the Procuring Organization under the tender documents and applicable law.

### No Subcontracting

No part of the Works shall be subcontracted to any third party. The Contractor shall be fully responsible for executing the Works using its own management, engineering, supervisory, labour, and construction resources. However, the Contractor may purchase materials, equipment, and other standard supplies from ordinary suppliers, and such purchases shall not be considered subcontracting.

### Site Engineer / Monitoring

AKRSP will depute a Site Engineer/designated Engineer to guide and monitor progress and quality, inspect works, verify measurements, witness tests and issue site instructions within delegated authority. Such monitoring does not transfer responsibility for the Works from the Contractor.

### Bid Preparation and Completeness

The bidder shall review all drawings, specifications, BoQ items and site information before pricing. The bid shall be based on the complete requirements of the tendered work and shall include all incidental work necessary for proper completion.

### Corrections and Alterations

Any correction, overwriting or alteration in the bid shall be clearly initialled by the authorized signatory. Unclear or unauthenticated alterations may be disregarded in accordance with the applicable procurement procedure.

### Confidentiality of Evaluation

Information relating to examination, evaluation and comparison of bids shall be handled confidentially in accordance with AKRSP procurement requirements. Bidders shall not seek to influence the evaluation process.

### Communication and Notices

All formal notices under the tender or Contract shall be made in writing through the registered email address stated in the BDS or Contract. The bidder shall promptly notify AKRSP of any change in its contact details.

### Contractor’s Own Costs

All costs of preparing, submitting and supporting a bid, including site visit and obtaining supporting documents, shall be borne by the bidder. AKRSP shall not be responsible for such costs.

## 1.1 Evaluation Principles

Bids will be evaluated in accordance with the stated Single Stage–Two Envelope bidding procedure. Technical/qualification evaluation shall be completed before any financial envelope is opened. Only bidders meeting the mandatory technical qualification requirements and whose bids are substantially responsive will proceed to financial evaluation.

Mandatory technical qualification requirements include valid PEC registration and at least two successfully completed similar civil works contracts, each exceeding PKR 50 million; average annual turnover exceeding PKR 200 million for the last three completed financial years; required personnel; adequate equipment/resources; acceptable method statement and programme; acceptable bid security; and tendered compilation.

A bid may be rejected as non-responsive where it contains a material deviation, reservation, omission, condition, price qualification, failure to provide required bid security, or other defect that materially affects the scope, price, quality, time or legal obligations.

Financial evaluation shall consider the total evaluated price of the complete tendered work, including applicable taxes, duties and other costs required under the tender. Arithmetic errors may be corrected in accordance with the tender procedure. The financial responsive bidder shall not automatically be awarded the Contract if required approvals, qualification verification or other mandatory requirements are not satisfied.

AKRSP may verify experience, turnover, tax/registration status, personnel and other submitted information. False, materially misleading or unverifiable information may result in rejection and any further action permitted under the Contract and applicable requirements.

## SECTION 2 – BID DATA SHEET (BDS)

| Item | Requirement |
| --- | --- |
| Implementing Partner | Aga Khan Rural Support Programme (AKRSP) |
| Project | Civil Works of Sonoghore Parwak 500 kW MHP |
| Tender Reference | CIVIL WORKS OF SONOGHORE PARWAK 500 kW MINI HYDROPOWER EU 2026 Hydropower Channel Portion-1 RD 00 to RD 2100 |
| Procurement Method | Single Stage – Two Envelope bidding procedure |
| Tendered work | Lot 1: Hydropower Channel Portion-1 (RD 00 to RD 2100 ) |
| Bid Language | English |
| Bid Currency | PKR |
| Tender Validity | 90 calendar days |
| Bid Security | PKR [1,760,000/-] |
| Time for Completion | [Oct30,2027] |
| Performance Security | 10% of Contract Price |
| Retention | 8% of interim payments, subject to Contract provisions |
| Defects Liability Period | 18 months (12 months after completion of tendered works & 6 months after operation of MHP) |
| Liquidated Damages | 0.1% of Contract Price per calendar day, maximum 10% |
| Advance Payment | None unless expressly stated in the Contract |
| Price Adjustment | Not applicable |
| Alternative Bids | Not permitted |
| Subcontracting | Not permitted |
| Clarification period regarding bid | Minimum 10 days before the bid submission dateline |
| Site Engineer | AKRSP-designated Site Engineer |
| Joint Venture [JV] | Joint Venture, Consortium, or Association bids shall not be permitted for this procurement. |
| Governing Law | Pakistan |
| Dispute Resolution | Good-faith negotiation followed by sole arbitration in Pakistan as provided in the Contract |
| EU Visibility | As required by the applicable EU financing arrangement and AKRSP instructions |

### Technical Qualification Requirements

| Requirement | Minimum Requirement | Evidence |
| --- | --- | --- |
| PEC Registration | C-4 or above with relevant civil works | Valid PEC registration certificate |
| Work Experience | At least two successfully completed similar civil works projects, each with contract value more than PKR 50 million, completed within the last 10 years | Contract/Work Order and Completion Certificate for each project |
| Financial Capability | More than PKR 200 million during the last three completed financial years | Audited financial statements or acceptable certified financial evidence |
| Staff Resources | One DAE civil site Engineer and one surveyor having 3 years of relevant experience | CVs and supporting documents |
| Company Equipment | Excavator: 1nos Mix Machine full bag: 2nos Vibrator machine :2nos Dumper/ Mazda :2 nos | Equipment list and ownership/hire evidence |
| Method statement | The bidder shall submit a method statement outlining the proposed methodology, work sequence, and resources for the execution of the works. |  |
| Detailed Implementation Schedule | The bidder shall submit a detailed implementation schedule for the tendered works, supported by a bar chart/Gantt chart indicating key activities, milestones, durations, and completion timelines. |  |

## SECTION 3 – BIDDING AND QUALIFICATION FORMS

Documents for compliancy

- Declaration of Undertaking (letter head only)

- Tender Security (Bid Bond)

Documents for technical qualification

The attached Envelope No. 1 (TECHNICAL BID DOCUMENTS) of our Tender contains:

- Bidder Information Form

- Valid Registration Status

- Work Experience in the last ten years

- Financial Capability

- Staff Resources

- Company’s Equipment

- Method Statement

- Implementation Schedule

Documents for Financial qualification

The attached Envelope No. 2 (FINANCIAL BID DOCUMENTS) of our Tender contains:

Letter of Bid

Provision of Rate analysis for each line item separately.

The priced Bill of Quantities

### Letter of Technical Submission

We, the undersigned, submit our Technical Qualification Documents for Lot 1.

| Item | Bidder Entry |
| --- | --- |
| Lot | ☐ Lot-1 Hydropower Channel Portion-1 (RD 00 to RD 2100 |
| Bidder Name | [ ] |
| Tender Reference | [ ] |
| Authorized Signatory | ____________________ |
| Name & Designation | ____________________ |
| Date | ____________________ |

### Bidder Information Form

| Particular | Information |
| --- | --- |
| Legal name of bidder | [ ] |
| Registered address | [ ] |
| Telephone & registered company email address | [ ] |
| NTN and STRN | [ ] |
| PEC registration status | [ ] |
| Authorized signatory | [ ] |

### Work Experience in Similar Civil Works

Provide at least two successfully completed similar civil works projects, each with a contract value more than PKR 50 million and completed within the last ten years.

| No. | Project / Client | Type of Work | Contract Value | Completion Date | Evidence/work order & completion certificate |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |

Similar works include irrigation channels, power channels, hydropower water conveyance channels, headrace/tailrace channels, lined/concrete water channels, intake/headworks, flood protection/channel structures and other comparable hydraulic civil works.

### Financial Capability

The bidder shall demonstrate an average annual construction turnover of at least PKR 200 million during the last three completed financial years, supported by audited financial statements.

| Financial Year | Turnover (PKR) | Supporting Document/ audit reports |
| --- | --- | --- |
| Average | ________________ | ________________ |

### Staff Resources

| Position | Minimum Experience | Name | Qualification [BE /DAE] |
| --- | --- | --- | --- |
| Civil Site Engineer | 3 years relevant experience |  |  |
| Surveyor | 3 years relevant experience |  |  |

### Equipment Resources

The bidder shall demonstrate availability of equipment adequate for timely completion of the project. Equipment may be owned or rental.

| Equipment | Type / Capacity | Quantity | Owned / rental |
| --- | --- | --- | --- |

### Method Statement

Submit a concise method statement covering mobilization, setting out, excavation, earthwork, concrete and masonry work, reinforcement where applicable, channel works, water management/dewatering, material supply, testing, quality control, safety and restoration/protection of affected areas.

### Implementation schedule

Submit a detailed implementation schedule for the said project in accordance with the project completion date provided in the BDS. Submit a practical bar & Gantt chart programme showing mobilization, major construction activities, testing/inspection and completion within the contractual period.

### Declaration of Undertaking

We, the undersigned, being the duly authorized representative of the bidder, hereby declare and undertake that:

- Eligibility and Legal Status
We confirm that our firm is legally registered and eligible to undertake the Works in Pakistan and possesses a valid PEC registration (C-4 or above) with the relevant category required for the Works.

- Accuracy of Information
All information, documents, certificates, experience records, financial information, personnel details and equipment information submitted with our bid are true, complete and accurate. We understand that any false, misleading or materially incorrect information may result in rejection of our bid, cancellation of award, termination of the Contract and/or other action permitted under the tender documents and applicable law.

- Compliance with Tender Requirements
We have carefully examined the complete tender documents, including the BDS, drawings, specifications, BoQ, addenda and other applicable documents, and confirm that our bid has been prepared in accordance with all stated requirements.

- Site and Scope of Works
We confirm that we have reviewed the available site information and understand the nature, scope, conditions and requirements of the Works. We accept responsibility for properly executing and completing the awarded Works in accordance with the Contract.

- Bid Security and Bid Validity
We confirm that the required Bid Security has been submitted in the prescribed form and amount and that our bid shall remain valid for the period specified in the BDS.

- No Subcontracting
We undertake that no part of the Works shall be subcontracted to any third party. The Works shall be executed using our own management, engineering, supervisory, labour and construction resources. We understand that ordinary purchase of materials and equipment from manufacturers, dealers or suppliers shall not constitute subcontracting.

- Joint Venture / Consortium
We confirm that this bid is submitted by our firm as a single bidder and is not a Joint Venture, Consortium or Association bid, in accordance with the BDS.

- Integrity and Prohibited Practices
We confirm that neither our firm nor, to the best of our knowledge, our representatives has engaged in or will engage in fraud, corruption, collusion, coercion, obstruction, misrepresentation or any other prohibited practice in connection with this procurement.

- Conflict of Interest
We declare that we have no actual or potential conflict of interest that would improperly affect our participation in this tender. We undertake to immediately disclose any conflict that may arise during the procurement or Contract period.

- Taxes and Statutory Compliance
We undertake to comply with all applicable federal, provincial and local tax laws and statutory requirements. We accept that applicable withholding taxes and other statutory deductions may be deducted by AKRSP from payments due to us and deposited with the relevant government authorities as required by law.

- Technical and Financial Requirements
We confirm that our firm meets the minimum technical, financial, experience, personnel and equipment requirements stated in the BDS and has submitted the required supporting evidence.

- Quality and Workmanship
We undertake to execute the Works in accordance with the approved drawings, technical specifications, BoQ, applicable standards and instructions issued by the authorized AKRSP Engineer, and to rectify defective or non-conforming work at our own cost where required under the Contract.

- Health, Safety and Environmental Requirements
We undertake to comply with applicable Pakistani laws and approved project requirements relating to occupational health and safety, labour, environmental protection and social safeguards. We shall provide appropriate PPE, safe working procedures, competent supervision and necessary safety arrangements at the Site.

- Programme and Completion
We undertake to mobilize adequate labour, equipment, materials and supervision and to complete the Works within the contractual Time for Completion specified in the BDS and Contract.

- Performance Security
If awarded the Contract, we undertake to provide the required Performance Security equal to 10% of the Contract Price in the prescribed form and within the period specified in the tender documents and Contract.

- Acceptance of Contract Conditions
We confirm our acceptance of the terms and conditions of the tender and undertake, if selected, to enter into the Contract and perform all contractual obligations in accordance with the tender documents and applicable laws of Pakistan.

- No Improper Influence
We undertake not to offer, give, request or accept any improper payment, benefit, gift or other inducement intended to influence the procurement, evaluation, award or administration of the Contract.

- Binding Undertaking
We understand that this Declaration of Undertaking forms part of our bid and that the commitments made herein shall be binding upon our firm. We acknowledge that any material breach of this Declaration may result in rejection of the bid, cancellation of award, termination of the Contract, forfeiture of applicable securities and/or other remedies available under the tender documents and applicable law.

We hereby certify that the above declarations and undertakings are true and correct to the best of our knowledge and belief.

Name of Bidder: __________________________________________

Registered Address: _______________________________________

NTN: _____________________________________________________

PEC Registration No.: _____________________________________

Name of Authorized Signatory: ______________________________

Designation: ______________________________________________

Signature: ________________________________________________

Company Seal: _____________________________________________

Date: ____________________________________________________

## SECTION 4 – BILL OF QUANTITIES (BoQ)

The Engineer’s Estimate / AKRSP internal cost is not part of the bidder-facing tender document. The BoQs below show only the quantities and descriptions required for bidding. The bidder shall enter unit rates and amounts for the selected Lot.

### 4.1 LOT 1 – Hydropower Channel Portion-1 (RD 00 to RD 2100)

| S.No. | Item Code | Description | Qty. | Unit | Bidder Rate (PKR) | Bidder Amount (PKR) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 03-12-d | Earth excavation in irrigation channels/drains & disposal up to 25m and dressing in shingle/gravel | 235,568 | cft |  |  |
| 2 | 19-25 | Providing and laying stone pitching/filling, dry hand packed in pitching & aprons | 3,791.667 | cft |  |  |
| 3 | 03-34-a | Filling and compacting soil, earth and boulders behind retaining walls (available material) | 33,179.73 | cft |  |  |
| 4 | 06-05-i | Plain cement concrete including placing, compacting, finishing & curing (1:4:8) | 4,513 | cft |  |  |
| 5 | 06-05-f | Plain cement concrete including placing, compacting, finishing & curing (1:2:4) | 6,946.5 | cft |  |  |
| 6 | 08-03-d-02 | Random rubble masonry in ground floor in cement/sand mortar (1:4) | 36,340.5 | cft |  |  |
| 7 | 06-44-b | PCC 1:3:6 in mass concrete less formwork using 40% boulders | 103,587.5 | cft |  |  |
| 8 | 11-09-b | Cement plaster 1:4 up to 20 ft height, 1/2 in thick | 17,688 | sft |  |  |
| 9 | 06-46-a | Erection and removal of formwork with wood surface finishing for RCC or plain cement concrete in any shape/position/horizontal | 30,600 | sft |  |  |
| 10 | 24-40 | Supply and fix PVC rubber water stopper, 8 in wide and 3/8 in thick, in vertical or horizontal expansion joints, complete | 512 | rft |  |  |

TOTAL BID PRICE: PKR ______________________________

### BOQ and Scope Clarification

The Contractor shall execute the Works shown in the approved BOQ, drawings and technical specifications for the awarded Lot. Any discrepancy affecting scope, quantities, drawings or interfaces shall be raised during the tender clarification period. No extra payment shall be due for work already covered by the Contract documents or reasonably necessary for proper completion of a specified item.

# PART II – IMPLEMENTING PARTNER’S REQUIREMENTS

## SECTION 5 – GENERAL SPECIFICATIONS

### General

The Works shall be executed in accordance with the approved drawings, specifications, BoQ, applicable standards and written instructions issued by AKRSP’s designated Engineer.

### Materials

All materials shall be of approved quality and suitable for their intended use. The Contractor shall obtain materials from reliable sources and shall provide test certificates where specified and required.

### Setting Out

The Contractor shall establish and maintain benchmarks, reference points, alignment, levels and chainages necessary for execution. Surveying shall be checked by the AKRSP Site Engineer/designated Engineer.

### Excavation

Excavation shall be carried out to the required lines, levels and dimensions. Unsuitable material shall be disposed of as directed. Excavated areas shall be protected from erosion, flooding and collapse.

### Rock Excavation

Where hard-rock excavation is included in the BoQ, excavation shall be carried out using methods suitable for the site and approved by the Engineer, with due protection of existing works, people and property.

### Concrete

Concrete shall be proportioned, mixed, placed, compacted, finished and cured in accordance with the approved specification. Formwork shall be rigid, properly aligned and adequately supported.

### Reinforcement

Reinforcement shall conform to the specified grade and shall be cut, bent, placed and secured in accordance with approved drawings. Cover shall be maintained using suitable spacers.

### Masonry

Stone masonry shall use sound, durable stone and approved mortar. Work shall be properly bonded, packed and cured, with joints and surfaces finished as specified.

### Channel Protection and Joints

Pitching, concrete, water stops, joints and other protection works shall be executed as shown in the drawings and BoQ. Work shall be protected against erosion and water damage.

### Testing and Inspection

The Contractor shall provide labour, equipment and samples necessary for testing. Work liable to be concealed shall not be covered until required inspection has been completed.

### Defective Work

Defective or non-conforming work shall be removed, repaired or replaced by the Contractor at its own cost as directed by the Engineer.

### Measurement

Measurements shall be taken in accordance with the BoQ and Contract provisions and shall be verified with the AKRSP Site Engineer/designated Engineer.

### Site Housekeeping

The Contractor shall maintain a reasonably clean, safe and orderly work site and shall remove waste, surplus materials and temporary works when no longer required.

### Site Access and Temporary Works

The Contractor shall arrange and maintain temporary access, working platforms, temporary drainage, dewatering, protection and other temporary works required for safe and efficient execution. Temporary works shall not damage adjoining land or existing infrastructure.

### Water Management

The Contractor shall plan and maintain suitable arrangements for diversion, drainage and dewatering so that excavation, concrete and masonry works can be carried out safely and to the required quality. The Works shall be protected from sudden flows and weather-related damage.

### Survey and Records

The Contractor shall maintain survey notes, levels, chainages, measurements, inspection requests, test results, material approvals and progress records. Records shall be made available to AKRSP on request.

### Concrete Quality

Aggregates, cement, water, mixing, placement, compaction and curing shall be controlled to achieve the specified concrete quality. Concrete shall not be placed against standing water or unsuitable surfaces unless an approved method is used.

### Curing and Protection

Fresh concrete, masonry, plaster and other vulnerable works shall be adequately cured and protected from excessive drying, freezing, impact, erosion and premature loading.

### Materials Testing

Where testing is specified, the Contractor shall arrange sampling and testing through an acceptable laboratory or testing facility. Test results shall be submitted to the Engineer promptly.

### Workmanship

All workmanship shall be neat, sound and fit for purpose. Lines, levels, dimensions, joints, surfaces and finishes shall conform to the approved drawings and specifications.

## Material Approval and Sources

Before incorporating materials into the Works, the Contractor shall submit the proposed source, manufacturer/supplier details where applicable, relevant certificates and samples when requested. Approval of a source does not relieve the Contractor from responsibility for the quality of each delivered batch. Materials failing the specified requirements shall be removed from the Site at the Contractor’s cost.

## Cement, Aggregates and Water

Cement shall be fresh, properly stored and of the type specified in the approved technical specifications. Fine and coarse aggregates shall be clean, hard, durable and free from harmful quantities of clay, silt, organic matter or other deleterious material. Mixing water shall be clean and suitable for concrete and mortar. Aggregates shall be properly graded as required for the approved concrete mix.

## Reinforcement Steel

Reinforcement shall comply with the grade, diameter, standard, bending, fixing and cover requirements shown in the approved drawings and technical specifications. Mill/test certificates shall be provided when required. Steel shall be stored above ground and protected from contamination and excessive corrosion.

## Concrete Quality and Testing

Concrete shall be produced using approved materials and the specified mix proportions or approved mix design. Batching, mixing, placing, compaction and curing shall be properly controlled. Slump and compressive-strength tests shall be carried out at the frequency directed by the Engineer or specified in the technical requirements. Concrete failing the specified strength or quality requirements shall be investigated and dealt with as directed by the Engineer, including removal and reconstruction where necessary.

## Masonry and Plaster

Stone for masonry and pitching shall be sound, durable and suitable for the specified work. Masonry shall be properly bonded, fully bedded in mortar and constructed to the lines, levels and dimensions shown in the drawings. Mortar shall be mixed in the specified proportion. Plaster shall have proper surface preparation, thickness and curing and shall be free from hollow or loose areas.

## Excavation, Over-Excavation and Disposal

Excavation shall be measured only within the lines, levels and limits shown in the drawings or directed by the Engineer. Excavation beyond the required profile due to the Contractor’s method, negligence or collapse shall not be paid for and shall be made good by the Contractor at its cost. Disposal locations shall be approved/identified by the Engineer. Suitable excavated material required for specified backfilling shall be preserved where practicable.

## Compaction and Backfilling

Backfilling shall be placed in suitable layers and compacted to the required density and moisture condition. The Engineer may require field density or other tests. No backfilling against structures shall be undertaken until the relevant work has been inspected and permission is given where required.

## Construction Joints and Water Stops

Construction and expansion joints shall be formed at the locations shown in the drawings. Water stops shall be installed continuously, securely and without damage, including proper cutting and jointing. Defective or displaced water stops shall be replaced at the Contractor’s cost.

## Inspection Before Concealment

The Contractor shall give reasonable notice before covering reinforcement, foundations, joints, water stops, embedded items or other work that will become inaccessible. Work covered without required inspection may be exposed at the Contractor’s cost.

## Quality Records

The Contractor shall maintain delivery records, material certificates, test results, concrete records, survey/measurement records, daily progress records and other quality records reasonably required for the Works. These records shall be available to the Engineer for verification.

## SECTION 6 – PARTICULAR / TECHNICAL REQUIREMENTS

### Lot 1 – Hydropower Channel Portion-1 (RD 00 to RD 2100)

The Lot comprises the defined first portion of the power/intake channel and associated civil structures shown in the approved drawings and BoQ. The Contractor shall complete all listed works within the stated chainage limits.

Earth excavation and disposal/dressing

Stone pitching and aprons

Backfilling and compaction behind retaining structures

PCC and mass concrete works

Random rubble masonry

Plastering and finishing

Formwork

Water stopper and expansion-joint works

Associated testing, curing, protection and ancillary works shown in approved documents

### Site Engineer

AKRSP will depute a Site Engineer/designated Engineer to guide and monitor progress and quality, inspect works, verify measurements, witness tests and issue instructions within delegated authority. The Contractor shall comply with lawful site instructions and shall remain responsible for the Works.

### Health, Safety and Environmental Protection

Provide appropriate PPE and safe working procedures.

Control excavation, lifting, machinery, vehicles, traffic, dust, noise, waste and fuel/oil spills.

Protect watercourses, roads, community property and public access.

Maintain warning signs, barricades and safe access around work areas.

Report serious accidents/incidents to AKRSP immediately.

Comply with applicable Pakistani laws and approved project environmental and social requirements.

# PART III – CONTRACT FORM AND CONDITIONS

## SECTION 7 – CONTRACT FORM

### Letter of Acceptance LOA

To: [                                    ]

We refer to your bid dated __________ for the Civil Works of Sonoghore Parwak 500 kW MHP, Lot __________. AKRSP hereby accepts your bid for the Contract Price of PKR __________, subject to the Bidding Document and Contract documents.

You are required to provide the Performance Security 10% and execute the Contract Agreement within the period stated in the BDS/Contract.

For and on behalf of AKRSP: ____________________   Name: ____________________   Date: __________

### Contract Agreement

This Agreement is made between Aga Khan Rural Support Programme (AKRSP) and the Contractor identified below for execution and completion of the Works of the selected Lot in accordance with the Bidding Document, accepted Bid, BoQ, drawings, specifications, addenda and this Contract.

| Item | Details |
| --- | --- |
| Contractor |  |
| Lot |  |
| Contract Amount |  |
| Time for Completion |  |
| Commencement Date |  |
| Defects Liability Period | 18 months (12 months after completion of tendered works & 6 months after operation of MHP) |
| Performance Security | 10% of Contract Price |

AKRSP: ____________________   Contractor: ____________________   Date: __________

### Order of Precedence

Contract Agreement / Letter of Acceptance

Addenda and written clarifications

Bid and Letter of Bid

Bid Data Sheet

Conditions of Contract

BoQ

Drawings and Technical Specifications

## Measurement and Payment – Detailed Requirements

The Works shall be measured and paid according to the units and quantities stated in the BoQ, based on the actual quantities of work satisfactorily completed, measured, verified and accepted by the Engineer/AKRSP at the corresponding accepted BoQ rates. The Contractor shall submit measurement records, invoices and supporting documents as required by the Engineer/AKRSP. Measurements shall, where practicable, be jointly checked with the AKRSP Site Engineer before inclusion in an Interim Payment Certificate.

Payment shall be made only against properly completed and accepted work. No payment shall be made for defective, incomplete, rejected or unauthorized work. No separate payment shall be made for labour, plant, transport, temporary works, setting out, curing, testing, protection, wastage, scaffolding, formwork, dewatering or other incidental requirements where these are included in an applicable BoQ item or are necessary for completion of that item and are not separately measured.

The Contractor shall submit interim payment applications with supporting measurements and records at the intervals specified by AKRSP. The Site Engineer shall verify the quantities and certify the amount payable, subject to retention money, withholding taxes, statutory deductions, recoveries, advances, penalties, Liquidated Damages and other lawful adjustments in accordance with the Contract and applicable laws.

Interim payments shall be treated as payments on account only and shall not constitute final acceptance or approval of the Works, nor relieve the Contractor of its obligation to rectify defects, omissions or non-compliant work identified during execution or the Defects Liability Period.

Payment shall not constitute acceptance of defective work and shall not prevent AKRSP from recovering amounts previously paid for quantities subsequently found to be incorrectly measured, duplicated, unsupported or otherwise not payable under the Contract.

## Final payment shall be made only after completion and acceptance of the Works and fulfillment of all contractual requirements. Claims and Notice

A Contractor claiming additional time or payment shall notify the AKRSP site engineer in writing as soon as reasonably practicable and, unless a different period is expressly stated in the Contract, within seven calendar days after becoming aware of the event giving rise to the claim. The notice shall briefly identify the event, its likely effect and the relief sought.

The Contractor shall maintain contemporaneous records supporting the claim and shall submit reasonable details and substantiation when requested. Failure to give timely notice or maintain supporting records may affect entitlement to the extent permitted by the Contract and applicable law. No claim shall be based solely on matters that were reasonably apparent from the tender documents or site inspection before bidding.

## Variations and Rate Determination

Only written variations instructed or approved by AKRSP through the authorized Engineer/representative shall be payable. Where a varied item is substantially similar to a BoQ item, the applicable BoQ rate shall be used where reasonable. For genuinely new work, the rate shall be agreed using comparable BoQ rates, supported resource analysis or other reasonable basis before the work is undertaken wherever practicable.

The Contractor shall not execute additional work on the basis of a verbal request and later claim payment unless the instruction is confirmed in writing by an authorized AKRSP representative.

## Materials on Site

Materials delivered to Site shall remain the Contractor’s responsibility until incorporated into the Works. Payment for materials not incorporated shall not be due unless the Contract expressly provides for it. The Contractor shall protect stored materials from damage, contamination, theft and weather.

## Final Measurement and Account

Before final payment, the Contractor shall submit final measurements, approved variation records, test results, completion/as-built information where required, and any other documents reasonably required to close the Contract. The final account shall be based on verified quantities and approved rates/variations.

## SECTION 8 – CONDITIONS OF CONTRACT

### Contractor’s Responsibility

The Contractor is fully responsible for proper execution, quality, safety, protection and timely completion of the awarded lot. AKRSP inspection or approval does not transfer this responsibility to AKRSP.

### Site Engineer

AKRSP will depute a Site Engineer to guide and monitor progress and quality, inspect works, verify measurements, witness tests and issue site instructions within delegated authority.

### Contractor’s Representative

The Contractor shall nominate a competent site representative who shall remain available at site and coordinate with the AKRSP Site Engineer.

### Commencement and Completion

The Contractor shall commence on the date stated in the Commencement Order and shall proceed continuously and diligently to complete the Lot within the Time for Completion.

### Programme and Progress

The Contractor shall submit a implementation schedule and maintain adequate labour, equipment and materials. Where progress falls behind, the Contractor shall immediately take effective corrective action.

### Extension of Time

Extension may be granted only for qualifying delays attributable to AKRSP, approved variations or Force Majeure, supported by timely notice and evidence.

### Liquidated Damages

If the Contractor fails to complete the Works within the contractual completion period, including any duly approved extension of time, due to reasons attributable to the Contractor, the Contractor shall be liable to pay liquidated damages at the rate of 0.1% of the Contract Price for each calendar day of delay.

Liquidated damages shall be deducted from amounts payable to the Contractor, including interim payments, retention money, or any other amount due under the Contract. The total amount of liquidated damages shall not exceed 10% of the Contract Price.

### Quality and Defects

Defective or non-conforming work shall be rectified promptly at the Contractor’s cost. The defects occurring during the Defect liability period [DLP] will be rectified by the contractor.

### Variations

No variation or additional work shall be executed without written instruction/approval by AKRSP. Unauthorized additional work shall not create an entitlement to payment.

### Performance Security

The successful Contractor shall furnish a Performance Security equivalent to 10% of the Contract Price in the prescribed form, issued by an acceptable bank or financial institution, within the period specified in the Contract.

The Performance Security shall remain valid for the period required under the Contract, including any extension necessary due to extension of the completion period or other contractual requirements. The Contractor shall ensure that the security remains valid and enforceable throughout the required period.

Failure to provide the Performance Security within the specified period shall constitute a breach of the Contract/condition of award and may result in cancellation of the award and such other contractual remedies as may be available to AKRSP.

The Performance Security may be invoked/forfeited, wholly or partially, in accordance with the Contract in the event of Contractor default, failure to perform contractual obligations, or failure to remedy an established contractual breach.

### Retention

Retention money shall be deducted at the rate of 8% of each certified Interim Payment and retained by AKRSP as security for the Contractor’s proper performance and fulfillment of its contractual obligations.

After 12 month upon completion of the tendered works and certification of completion by the Engineer/AKRSP, 50% of the total accumulated retention money shall be released to the Contractor, subject to satisfactory completion and acceptance of the works and settlement of any outstanding recoveries or contractual obligations.

The remaining 50% of the accumulated retention money shall be released six (6) months after the testing and commissioning of the MHP Project, subject to satisfactory performance of the completed works, rectification of any defects attributable to the Contractor, and fulfillment of all outstanding contractual obligations.

No retention shall be released to the extent required to cover any outstanding defects, recoveries, damages, or other amounts lawfully due from the Contractor under the Contract.

### Advance Payment

No advance payment shall be made as specified in the BDS.

### Insurance and Liability

The Contractor shall maintain required insurance and shall remain responsible for loss, damage, injury and claims arising from its operations, except where the Contract expressly places responsibility on AKRSP.

### Records and Access

The Contractor shall maintain site records, measurements, test results and progress records and make them available to AKRSP.

### Suspension

AKRSP may instruct suspension where necessary for safety, quality, design clarification or other legitimate project reasons. The Contractor shall protect the Works during suspension.

### Termination for Contractor Default

If, during execution of the Works, the Contractor fails to perform its contractual obligations or fails to rectify any notified deficiency within the required time, AKRSP may issue two written notices by email to the address provided in the Bidder Information Form, allowing a minimum of 15 calendar days between the two notices.

If the Contractor fails to take satisfactory corrective action following the second notice, AKRSP may terminate the Contract by written notice through the registered email address of the Contractor, in accordance with the Contract.

All contractual notices, instructions, correspondence and communications between AKRSP and the Contractor shall be made through the registered email addresses provided in the Contract/Bidder Information Form and shall be considered official communication.

### Immediate Termination

AKRSP may terminate the Contract with immediate effect by written notice if the Contractor commits a serious breach, including abandonment of the Works, unauthorized subcontracting, fraud or corruption, insolvency, serious safety violations, persistent or serious substandard workmanship, or any other material breach where immediate termination is reasonably necessary to protect the Project, AKRSP, workers, or the public.

Such termination shall be without prejudice to AKRSP’s other contractual or legal rights and remedies, including recovery of any losses or costs arising from the Contractor’s default.

### Consequences of Termination

Following termination for Contractor default, AKRSP may take possession of the Site and Works and arrange completion through another contractor or other lawful means. Subject to applicable law and the Contract, the Contractor shall be liable for reasonable additional completion costs and other losses arising from its default. AKRSP may recover amounts due from the Performance Security and sums otherwise payable to the Contractor.

### Termination for Project Reasons

AKRSP may terminate the Contract for project or funding reasons by written notice where permitted by the applicable financing arrangement and Contract. The Contractor shall be paid for properly executed and accepted work and other amounts expressly due, subject to lawful deductions.

### Force Majeure

Force Majeure means an exceptional event beyond the reasonable control of the affected party that materially prevents performance and could not reasonably have been prevented or overcome. The affected party shall notify AKRSP promptly and minimize its effects.

### Dispute Resolution

The parties shall first attempt in good faith to resolve disputes through direct discussion. If unresolved for 28 days, the dispute may be referred to a sole arbitrator mutually agreed by the parties or appointed in accordance with applicable Pakistani law. The seat shall be in Pakistan and proceedings shall be in English.

### Governing Law

The Contract shall be governed by the laws of Islamic Republic of Pakistan.

### Donor Visibility

The Contractor shall follow AKRSP instructions concerning project signage, acknowledgement and other visibility measures required under the applicable European Union financing arrangement.

### Site Possession and Access

AKRSP shall provide access to the Site to the extent reasonably available for the Works. The Contractor shall keep access routes and working areas orderly and shall coordinate its activities so as not to unnecessarily obstruct public movement.

### Contractor’s Equipment and Resources

The Contractor shall mobilize and maintain sufficient labour, supervision, plant, tools, equipment and materials for timely completion. AKRSP may require replacement of inadequate resources where they materially affect progress or quality.

### Protection of Works and Property

The Contractor shall protect the Works, existing structures, roads, watercourses, public property and adjacent land from damage caused by its operations. Any damage caused by the Contractor shall be repaired at its cost.

### Inspection and Tests

The Engineer may inspect materials and workmanship at any reasonable time. The Contractor shall provide access, assistance, samples and records required for inspection and testing. Inspection does not relieve the Contractor of its obligations.

### Taking Over

When the Works are substantially complete and fit for their intended use, the Contractor may request Taking Over. AKRSP shall inspect the Works and identify any outstanding defects or minor items to be completed before or after Taking Over, as appropriate.

### As-Built Information

Where required by the Engineer, the Contractor shall provide simple as-built drawings, survey information and records showing material changes from the approved drawings. These shall be submitted before final completion.

### Final Account

The Contractor shall submit its final measurement and payment documentation in the form required by the Contract. Final payment shall be subject to verification of quantities, completion of required documents and lawful deductions.

### Survival of Obligations

Obligations concerning defects, confidentiality, records, indemnity, payments, taxes and other matters intended by their nature to continue shall remain effective after completion or termination to the extent required by the Contract or applicable law.

# PART I – FINANCIAL BID FORMS

## SECTION 9 – FINANCIAL BID FORMS

### Letter of Bid

Date: __________

To: Aga Khan Rural Support Programme (AKRSP)

We, the undersigned, offer to execute and complete ONE Lot only in conformity with the Bidding Document.

| Item | Bidder Entry |
| --- | --- |
| Selected Lot | ☐ Lot 1 – Hydropower Channel Portion-1 (RD 00 to RD 2100) |
| Total Bid Price | PKR ____________________ |
| Bid Validity | 90 calendar days |

We confirm that our bid is complete, that the prices include all costs required for completion, that we accept the Contract conditions, and that no part of the Works will be subcontracted.

Authorized Signatory: ____________________   Name: ____________________   Company Seal: __________   Date: __________

### Priced Bill of Quantities

The bidder shall complete the BoQ for the selected Lot. The bidder shall not alter the stated quantities except where expressly permitted by the tender documents.

### Performance Security

The successful bidder shall provide a Performance Security equal to 10% of the Contract Price in the prescribed form and within the period stated in the Contract.

# PART IV – SCOPE OF WORKS AND DESIGN INFORMATION

## SECTION 10 – SCOPE OF WORKS AND DESIGN INFORMATION

### Scope of Lot 1

Lot 1 covers the first portion of the Hydropower channel from RD 00 to RD 2100 and the associated channel civil structures included in the approved BoQ and drawings.

### Drawings and Design Information

The approved tender drawings, design calculations where applicable, technical specifications and other design information issued by AKRSP shall form part of the tender documents.

Drawing Register:

| Drawing No. | Title | Revision | Date |
| --- | --- | --- | --- |

### 10.4 Technical Specifications Register

| Specification No. | Description | Revision |
| --- | --- | --- |

# ANNEX A – LABOUR, OHS AND ENVIRONMENTAL REQUIREMENTS

These requirements are intentionally practical. The Contractor remains responsible for compliance with applicable Pakistani laws and approved project environmental and social requirements.

Comply with applicable labour, environmental and occupational safety requirements.

Provide suitable PPE, safe work procedures, competent supervision, first aid and basic emergency arrangements.

Control excavation, work at height, lifting, machinery/vehicles, traffic, dust, noise, waste, wastewater and fuel/oil spills.

Protect watercourses, roads, community property and public access.

No child labour, forced labour, discrimination, harassment, sexual exploitation/abuse or gender-based violence.

Maintain warning signs, barricading and a reasonably safe and clean work site.

Report serious accidents/incidents to AKRSP immediately.

Before commencement, submit a short site safety plan covering major hazards, PPE and emergency arrangements.

Contractor Acknowledgement: ____________________   Authorized Signatory: ____________________

Date: __________